## README
LibreDAB — Planning Pack (block diagram, BOM, size & risk)
Open-source GaN, 1 MHz Dual Active Bridge — Sodium-Ion battery <-> 400 V DC link, 800 W
Status | Planning stage. Figures are first-pass estimates to be confirmed in detailed design + prototype.
Prepared | Initial pass, June 2026
Locked decisions | Full-bridge both sides; SPIN as plug-in controller; series L from transformer leakage; cooling sized from thermals.
Confidence legend | H = high (datasheet/quote), M = medium (engineering estimate), L = low (rough / needs prototype)
Colour legend | Blue cells = inputs you can change. Black = calculated/text. Yellow = key assumption.
FX assumption | GBP per USD used for converting USD-quoted parts (see Cost_Summary, change in one place).
Sheets
Design_Calcs | DAB operating points, required series inductance, transformer flux density & leakage feasibility.
Loss_Thermal | Loss budget at nominal and worst-case corner; efficiency; cooling recommendation.
BOM | Line-by-line bill of materials with sources (LCSC / UK-custom / off-LCSC), costs and references.
Cost_Summary | Roll-up by category, per-board total and low/high range.
Size_Estimate | Area budget against the 70 x 280 mm single-sided board; Z-height note.
Risk_Register | Ranked risks with likelihood x impact and mitigations.
References | All sources with URLs (every checkable figure is traceable here).
IMPORTANT | GaN power devices (LMG2100R026, LMG2652) are NOT in the LCSC catalogue. They are off-LCSC lines
(Mouser/DigiKey/TI) - now an all-TI power stage (single vendor). All-LCSC HV fallback (Tokmas CID12N65D x4 + drivers) noted in BOM.

## Design_Calcs
DAB Design Calculations (single-phase-shift model)
Topology assumption: full bridge both sides, battery = primary (1T), DC link = secondary (11T)
Inputs (blue = change)
Battery nominal voltage | 42 | V
Battery minimum voltage | 23.8 | V
Battery maximum voltage | 58.8 | V
DC link voltage | 400 | V
Rated power | 800 | W
Switching frequency | 1000000 | Hz
Turns ratio n = Ns/Np | 11 | -
Primary turns Np | 1 | -
Core A_L (assembled pair) | 3.7e-06 | H
Core effective area Ae | 0.000146 | m^2
Design phase shift (nominal) | 50 | deg
Assumed efficiency (for current calc) | 0.95 | -
Primary RMS factor (x I_dc, rough) | 1.2 | -
Calculations
Secondary turns Ns | 11 | -
Reflected link voltage to primary (Vlink/n) | 36.3636 | V
Battery current at nominal | 19.0476 | A
Battery current at min V (incl. eff.) | 35.3826 | A
Phase shift (radians) | 0.87266 | rad
Phase shape factor φ(1-φ/π) | 0.63026 | -
REQUIRED series inductance, referred to primary | 1.915e-07 | H
= required series inductance (primary) | 191.4983 | nH
= required series inductance (secondary) | 23.1713 | uH
Magnetizing inductance (primary) | 3.7e-06 | H
Required leakage as % of magnetizing | 5.176% | %
Peak flux density (secondary, square-wave approx) | 0.062267 | T
= peak flux density (secondary) | 62.2665 | mT
Peak flux density (primary, approx) | 71.9178 | mT
Primary RMS current at nominal | 22.8571 | A
Primary RMS current at min-V corner | 42.4591 | A
Interpretation
Required leakage (~5% of magnetizing) is HIGH for a tightly-coupled RM transformer (typical 1-3%).
Achieving AND controlling this with a single-turn primary is the dominant magnetics risk (see Risk M-01).
Flux density ~60-72 mT at 1 MHz in N49 is acceptable but core loss is non-trivial (see Loss_Thermal).
Battery range 23.8-58.8 V is a 2.47:1 swing -> reflected 262-647 V vs fixed 400 V link; ZVS range and RMS
currents vary strongly with state-of-charge. Adaptive modulation likely needed (Risk C-01).
Required series L scales with design phase shift (blue input row 15); lower phase shift -> lower L needed.

## Loss_Thermal
Loss Budget & Thermal Recommendation
Efficiency target >95% at NOMINAL (42 V, 800 W). Worst case = 23.8 V / full power.
Block | Loss @ nominal (W) | Loss @ worst corner (W) | Confidence | Basis / source
LV full bridge (2x LMG2100R026, 2.6 mΩ) | 5 | 11 | M | Lower Rds (2.6 mΩ) cuts conduction; 53 A rating eases low-V corner
HV full bridge (2x LMG2652, 140 mΩ) | 5 | 7 | M | Low HV current; 650 V ZVS switching dominates at 1 MHz
HF transformer (core + copper) | 4 | 6 | M | N49 ~60-72 mT @1 MHz; user est 2 W is optimistic
Bias / gate drive / control | 2 | 3 | M | Gate charge x f, aux supply, sensing
PCB / interconnect / connectors | 2 | 4 | L | I^2R in copper at 19-35 A on LV side
TOTAL LOSS | 18 | 31
Output power (W) | 800
Estimated efficiency | 97.8% | 96.27%
Cooling recommendation (sized from thermals)
Worst-case ~40 W (low-SoC, full power) over a 70x280 mm (196 cm^2) single-sided board.
Natural convection alone (~10-20 W at acceptable rise) is INSUFFICIENT at the worst corner.
RECOMMENDED: conduction to a chassis/baseplate as the main heat path, plus a screw-mounted
top-side heatsink bar over the LV stage (EPC23102 has an exposed-TOP cooling pad - ideal, removable).
HV stage (LMG2652) is bottom-cooled: thermal vias to a bottom plane -> gap pad -> chassis.
Provide footprint/headers for an optional small fan for continuous worst-corner operation.
This satisfies the repairability rules: single-sided placement, screwed (not potted) heatsinks.

## BOM
Bill of Materials (per board, low-volume / prototype pricing)
Sources: LCSC (PCBway-orderable) unless noted UK-custom or off-LCSC. Costs in GBP.
# | Block | Function / Ref | Part number | Mfr | Source | Qty | Unit £ | Ext £ | Quoted price (native) | Datasheet / link | Conf. | Notes
1 | LV bridge | HS+LS GaN half-bridge x2 (full bridge) | LMG2100R026 | TI | off-LCSC (Mouser/DigiKey) | 2 | 8 | 16 | ~$8-13 low qty; in stock | https://www.ti.com/product/LMG2100R026 | M | 93V cont/100V pulsed, 53A, 2.6 mOhm, top-cooled. All-TI w/ HV. NOT on LCSC
2 | HV bridge | HV GaN half-bridge x2 (full bridge) | LMG2652RFBR | TI | off-LCSC (Mouser/DigiKey) | 0 | 6 | 0 | ~$7-8; 12-wk lead | https://www.ti.com/product/LMG2652 | M | Integrated driver+current sense; bottom-cooled; 12-wk lead
3 | HV bridge (ALT) | All-LCSC HV fallback: single switch x4 + drivers | CID12N65D | Tokmas | LCSC C21547657 | 4 | 0.5 | 2 | $0.6276 LCSC | https://www.lcsc.com/product-detail/C21547657.html | M | Alternative path: needs 4 x modules instead of 2 x
4 | Magnetics | RM12 core set (N49) | B65815E0000R049 | TDK/EPCOS | UK (Farnell/TME) - custom | 1 | 8 | 8 | ~£6-12/pair | https://uk.farnell.com/epcos/b65815e0000r049/transformer-core-rm-n49-57mm/dp/4167325 | M | A_L 3700 nH, Ae 146 mm^2, sold as pair
5 | Magnetics | RM12 coil former (bobbin) + clips | RM12 bobbin/clip set | TDK/EPCOS | UK - custom | 1 | 4 | 4 | ~£3-5 | https://www.tdk-electronics.tdk.com/inf/80/db/fer/rm_12.pdf | M | Required to wind transformer
6 | Magnetics | Litz wire (primary heavy + secondary) | Litz 12A & 3A | RM Cybernetics | UK - custom | 1 | 15 | 15 | ~£10-25 | https://www.rmcybernetics.com/ | L | Single-turn primary at ~40 A RMS may need paralleled bundles
7 | Magnetics | Transformer winding / assembly (custom labour) | Custom wound RM12 | UK winder | UK - custom | 1 | 25 | 25 | ~£15-50 | https://www.rmcybernetics.com/ | L | Leakage must be tuned & measured; biggest cost uncertainty
8 | HV cap | DC-link bus capacitance (C0G/film, 500-630 V) | ceramic/film array | various | LCSC | 1 | 8 | 8 | allowance | https://www.lcsc.com/ | M | High-freq bus decoupling near HV bridge
9 | LV cap | Battery-side bulk + decoupling (high ripple) | ceramic + polymer | various | LCSC | 1 | 8 | 8 | allowance | https://www.lcsc.com/ | M | Ripple current rating critical at 1 MHz / 35 A
10 | Sensing | Battery current sense (shunt + isolated amp or Hall) | e.g. TMCS/INA-class | various | LCSC | 1 | 5 | 5 | allowance | https://www.lcsc.com/ | M | HV current available from LMG2652 integrated sense
11 | Sensing | Voltage dividers + scaling buffer (both sides, 0-2.048 V) | resistors + op-amp | various | LCSC | 1 | 3 | 3 | allowance | https://www.lcsc.com/ | M | Conditioned to SPIN ADC 0-2.048 V range
12 | Bias | Aux/isolated supply + LDOs (5 V / VDD rails) | iso DC-DC + LDO | various | LCSC | 1 | 6 | 6 | allowance | https://www.lcsc.com/ | M | Powers GaN gate-driver bias on both domains
13 | Interface | Battery connector (35 A rated) | screw terminal / high-current | various | LCSC | 1 | 4 | 4 | allowance | https://www.lcsc.com/ | M | Repairable, re-mountable per golden rules
14 | Interface | 400 V link connector | >600 V rated | various | LCSC | 1 | 3 | 3 | allowance | https://www.lcsc.com/ | M
15 | Interface | SPIN header (2.54 mm) | pin header | various | LCSC | 1 | 2 | 2 | allowance | https://www.owntech.org/spin-2/ | H | PWM out + ADC in (0-2.048 V) + serial/analog ref
16 | Interface | Test points (all major nets) | SMD test points | various | LCSC | 1 | 2 | 2 | allowance | https://www.lcsc.com/ | H | Golden rule: TPs on all major power & control nets
17 | Indicator | 'No Error' status LED + driver | LED + transistor | various | LCSC | 1 | 1 | 1 | allowance | https://www.lcsc.com/ | H | Absence of indication = error
18 | Passives | Gate Rs, bootstrap caps, decouplers, dividers | 0402/0603 passives | various | LCSC | 1 | 5 | 5 | allowance | https://www.lcsc.com/ | M | Min. part diversity per golden rules
19 | Thermal | Top-side heatsink (LV) + TIM + screws | heatsink+pad | various | UK/LCSC | 1 | 6 | 6 | ~£4-10 | https://www.lcsc.com/ | L | Screw-mounted, removable
20 | PCB | 4-layer 2 oz, 70 x 280 mm (qty 5 amortised) | custom PCB | PCBway | PCBway | 1 | 20 | 20 | ~£12-35/board | https://www.pcbway.com/orderonline.aspx | L | 2 oz copper + large area push cost up; use PCBway calculator
[7 empty] | PER-BOARD TOTAL | 143
Note: ALT row (Tokmas) qty set to 0 so it is excluded from the total; switch quantities to swap the HV path.

## Cost_Summary
Cost Summary (per board)
FX assumption: GBP per USD | 0.79 | (=1/1.27; used where parts quoted in USD)
Category | Cost £ | Confidence | Comment
Semiconductors (GaN) | 16 | M | LMG2100R026 x2 + LMG2652 x2; all-TI, off-LCSC
Magnetics (custom, UK) | 52 | L | Core+bobbin+litz+winding; dominant uncertainty
Capacitors | 16 | M | HV bus + LV bulk/decoupling
Sensing & control interface | 26 | M | Current/voltage sense, bias, connectors, TPs, LED
Misc passives | 5 | M | Gate Rs, bootstrap, dividers
Thermal | 6 | L | Heatsink + TIM
PCB (PCBway) | 20 | L | 4-layer 2 oz, 70x280 mm
POINT-ESTIMATE TOTAL | 141
Range factors (blue)
Low factor | 0.75
High factor | 1.55
Estimated low (£) | 105.75
Estimated high (£) | 218.55
Overall cost confidence: M-L. Drivers of spread: custom transformer, low-qty GaN pricing, PCB area/copper.

## Size_Estimate
Size Estimate vs 70 x 280 mm target
Board area available (single-sided) | 196 | cm^2 (=196)
Block | Approx area (cm^2) | Conf. | Notes (footprint basis)
LV full bridge + input caps | 22 | M | 2x LMG2100R026 (7x4.5 mm) + decoupling + heavy-copper pour
HV full bridge + bus caps | 22 | M | 2x LMG2652 (6x8 mm) + 400 V bus caps
HF transformer (RM12) | 18 | M | Core ~37.6x29.8 mm + clearance; tallest part ~25 mm
Sensing + bias + control interface | 25 | M | Dividers, current sense, aux supply, SPIN header
Connectors + test points | 18 | M | Battery (35 A) + 400 V link + TPs
Isolation barrier / creepage gap | 20 | M | 400 V <-> battery separation under/around transformer
Routing / margin | 35 | L | Spacing, vias, keep-outs, single-sided routing overhead
TOTAL allocated | 160
Spare vs 196 cm^2 | 36
Verdict: fits the 70x280 mm footprint with modest margin (conf M). Z-height is set by the RM12
core (~25 mm) plus the top-side heatsink, so the module depth - not PCB area - is the tighter constraint.

## Risk_Register
Risk Register
Likelihood (L) & Impact (I) on 1-5 scale; Score = L x I. Higher = attend first.
ID | Category | Risk | L | I | Score | Mitigation | Status
M-01 | Magnetics | Leakage-only series L (~5% of magnetizing, single-turn primary) hard to hit AND control; sets power transfer | 4 | 4 | 16 | Design winding separation for target leakage; measure & tune on prototype; keep discrete shim inductor as fallback | Open
T-01 | Thermal/Device | LV switch current at 23.8 V full-power corner (~42 A) vs 53 A rating -> comfortable margin; thermal still to manage | 2 | 3 | 6 | Top-side heatsink + conduction; verify 1 MHz thermal derating at worst corner | Open
S-01 | Sourcing | GaN power ICs not on LCSC (EPC23102) / LMG2652 12-wk lead -> not fully PCBway-assemblable | 4 | 3 | 12 | Dual-source; pre-order long-lead; all-LCSC Tokmas HV path; consign parts to PCBway | Open
L-01 | Layout/EMI | 1 MHz GaN gate loops, switching-node ringing, conducted/radiated EMI | 4 | 3 | 12 | Tight power-loop layout; follow EPC/TI ref designs; slew-rate control; input/output filtering | Open
I-01 | Isolation | 400 V <-> battery isolation incl. sensing & gate-drive references and PCB creepage | 3 | 4 | 12 | Define isolation standard; PCB creepage/clearance; isolated sense & bias across barrier | Open
C-01 | Control | Wide 2.47:1 battery range degrades ZVS range & raises RMS currents at SoC extremes | 3 | 3 | 9 | Adaptive modulation (extended-phase-shift / triangular) in SPIN firmware; verify ZVS map | Open
E-01 | Efficiency | Meeting >95% at 1 MHz once real core, AC-copper, gate & ringing losses are included | 3 | 3 | 9 | Refine loss model; optimise magnetics & ZVS; treat >95% as nominal-point target | Open
M-02 | Magnetics | Custom hand-wound transformer: cost, lead time and unit-to-unit repeatability | 3 | 3 | 9 | Document winding spec; qualify a UK winder; characterise L_leak & losses per unit | Open
P-01 | PCB | 35 A on LV side: copper heating, via current, thermal coupling to devices | 3 | 3 | 9 | 2 oz (or heavier) copper, large pours, paralleled layers, thermal vias | Open
R-01 | Repairability | GaN QFNs (incl. exposed-pad) are hard to hand-rework vs golden rules | 2 | 3 | 6 | Single-sided placement; hot-air-reworkable layout; spacing; full test points | Open
X-01 | Caps | LV bus ripple-current rating at 1 MHz / high current | 2 | 3 | 6 | Ceramic arrays with adequate ripple rating; verify thermals | Open
D-01 | Control/Spec | Bidirectional reference (analog OR serial) + 'no-error' logic complexity | 2 | 3 | 6 | Leverage OwnTech SPIN stack; staged firmware bring-up; clear fault state machine | Open

## References
References (all checkable)
# | Source | Supports | URL
1 | TI LMG2100R026 product page | LV GaN: 93 V cont/100 V pulsed, 53 A, 2.6 mΩ, integrated driver, top-cooled | https://www.ti.com/product/LMG2100R026
2 | TI LMG2100R026 datasheet (PDF) | Electrical specs, 7.0x4.5 mm 18-VQFN, UVLO/clamp protection | https://www.ti.com/lit/ds/symlink/lmg2100r026.pdf
3 | DigiKey LMG2100R026VBNR | Availability (in stock) & low-qty pricing - verify before order | https://www.digikey.com/en/products/detail/texas-instruments/LMG2100R026VBNR/25811484
4 | TI LMG2652 product page | HV GaN: 650 V, 140 mΩ, integrated driver+sense, bottom-cooled | https://www.ti.com/product/LMG2652
5 | DigiKey LMG2652RFBR | Availability / 12-week lead, 19-VQFN 8x6 mm | https://www.digikey.com/en/products/detail/texas-instruments/LMG2652RFBR/26251057
6 | LCSC CID12N65D (Tokmas) | All-LCSC HV fallback, 650 V, from $0.6276 | https://www.lcsc.com/product-detail/C21547657.html
7 | Farnell B65815E0000R049 | RM12 N49 core, UK source | https://uk.farnell.com/epcos/b65815e0000r049/transformer-core-rm-n49-57mm/dp/4167325
8 | TME B65815E0000R049 | A_L 3700 nH, Ae 146 mm^2, sold as pair | https://www.tme.eu/en/details/b65815e0000r049/ferrite-cores/epcos/
9 | TDK RM12 datasheet | A_L by grade (N49 = 3700 nH +30/-20%) | https://www.tdk-electronics.tdk.com/inf/80/db/fer/rm_12.pdf
10 | RM Cybernetics | UK Litz wire (12 A / 3 A variants) | https://www.rmcybernetics.com/
11 | OwnTech SPIN | Controller: STM32G4, HRTIM PWM, ADC 0-2.048 V | https://www.owntech.org/spin-2/
12 | OwnTech ADC docs | ADC input range 0-2.048 V, PWM-triggered sampling | https://docs.owntech.org/latest/examples/SPIN/ADC/adc_hrtim_trigger/
13 | LibreSolar BMS C1 | 60 V max -> sets 14S Na-ion upper limit | https://github.com/LibreSolar/bms-c1
14 | PCBway online quote | PCB fabrication cost calculator | https://www.pcbway.com/orderonline.aspx